## Slide 1
Austin Stack
Asst. Governor Wheatfield Prison
AUSTIN STACK ACJRD 21/01/13

## Slide 2
Strategic Action 3
Action
“We will examine the possibility of introducing on a pilot basis, restorative justice practices in a prisons context”
Strategic Outcome
To provide prisoners with another avenue to:
Address & take responsibility for their offending behaviour
Make reparations to the community
Raise victim awareness among the prison population
AUSTIN STACK ACJRD 21/01/13

## Slide 3
Establishment of a Strategy Team
Pilot Locations: Wheatfield & Dochás
Research & Networking
RJ Policy
Training Plan
Governor Group
AUSTIN STACK ACJRD 21/01/13

## Slide 4
Planning Phase
RJ Multi-Disciplinary Group
What RJ Practices can be delivered
Training Requirements
Which parts of the Prison
AUSTIN STACK ACJRD 21/01/13

## Slide 5
RJ Multi-Disciplinary Group
Governor
A/Governor
Psychology
Probation
Chaplaincy
AUSTIN STACK ACJRD 21/01/13

## Slide 6
What RJ Practices can be delivered
Conflict Awareness/Resolution
P19s (Disciplinary Adjudications)
Community Reparation
Victim/Offender Conferencing (review after 12 months)
AUSTIN STACK ACJRD 21/01/13

## Slide 7
Training Requirements
One Day Conflict Awareness/RJ Awareness
Three Day RJ Conference Facilitator Training
One Day Governor Training
Prisoner Information/Awareness
AUSTIN STACK ACJRD 21/01/13

## Slide 8
Training Requirements- Who
Multi-D Group
Class Officers
Asst. Chief Officers
Chief officers
Governors
AUSTIN STACK ACJRD 21/01/13

## Slide 9
Which Parts of the Prison
5G (30 inmates)
10F (30 inmates)
10G (30 inmates) after initial 3 months
AUSTIN STACK ACJRD 21/01/13

## Slide 10
Timelines
Awareness Training- end of Feb 2012
RJ Facilitator Training- mid March 2012
Governor Training day- end of March 2012
Prisoner information- end of March 2012
Launch- Start of April 2012
AUSTIN STACK ACJRD 21/01/13

## Slide 11
Evaluation
Fix the problems
Continue to Research/Network/Learn
Roll out to other prisons
Promote RJ on an ongoing basis
AUSTIN STACK ACJRD 21/01/13

## Slide 12
AUSTIN STACK ACJRD 21/01/13
For More Information
e-mail: adstack@irishprisons.ie
Phone: 01-6209488
Mobile: 087-9855302
@adstack68
Austin Stack
Thank You